## Sheet1
Section | Task | Description | Track Finish Date
Vendor | Complete Vendor Model file | Update all of the functions for the model file for vendors. So all of the data is ready to be pulled. | 2016-12-30
Vendor | Create Manage Users Page | Create a page to manage additional vendor users for vendors | 2016-12-31
Vendor | Create Manage Business Page | This page is what initially is loaded for a vendor. It shows listings of all of the businesses they can manage including a manage button. It gets if they are a premium member and their business basic information just for presentation purposes. This also includes editing their business information such as hours, description, and keywords. | 2017-01-01
Vendor | Create Manage Business Information Page | This page is once you get into the vendor business. This shows all of the basic options they can do such as edit their business information. As well as add photos. | 2017-01-03
Vendor | Create Manage Promos Page | This page gets all the promotions and posts they made for consumers feeds. It will allow them to update any text, and image they would like to add. Like a facebook post. It will allow them to delete any old posts they may have made in the past. | 2017-01-04
Vendor | Create PPC Campaign Pages | If the user is a premium member alllow them to add credit to their account. As well as create a pay per click campaign with as many keywords as they want. With the ability to delete campaign, make it inactive, add/edit/remove keywords. | 2017-01-08
Vendor | Create Reports Page | The reports page will get business review stats, business stats general, ppc stats if applicable, rating stats, mobile app stats, and web stats. All of this is for premium members with the exception of some basic statistical data which counts as business stats general. | 2017-01-13