## Sheet1
Section | Task | Description | ETA Hours Required
Vendor | Create a subscription signup page | This page will draw the users to our services as a premium member. It will layout all the qualities of being a premium member then a regular member. It will also have a signup for month to month, 3 month, 6month, and 1 year subscription. As we will promote signing up for 1 year at a time with a recurring subscription billing setup. | shit
Website | Update restaurant profiles | I will need to update the restaurant profiles to show anything that’s missing, menu items, review responses, follow button for consumers, photos, etc. | 0
Website | Create where are you page | If I cannot accurately get where somebody is by their zipcode initially I will bounce them to a page that requires them to submit where they are. | 0
Consumer | Update profile page | Make sure users can upload photos of themselves as profile pictures for their avatar, update their bio, remove followed restaurants, add followed restaurants. | 0
Consumer | Update feed page | Create the feed page for information of coupons, deals, of people the consumer followed in chronological order. | 0
Consumer | Reviews Check | Make sure consumers can leave reviews, get activated accounts, and that anonymous people can leave reviews on restaurant page. | 0
Testing | Test the website as a whole | Test each page, consumer, vendor, website. Test all functionalities. Go over everything and anything. Double check for bugs. | 0
Social Media | Update all social medias | Submit announcements that we will be launching soon. Specify date, update all additional information needed on social platforms. | 0
Company | Soft Launch | We will be launching our website into the public atmosphere of the interwebs. This is a soft launch so we will not be doing extreme mass marketing to promote the site until we get some initial feedback. Marketing comes with dates listed below in time schedule. | 1/0/1900
1. Purchase dedicated server
2. Purchase side shared unlimited hosting plan for images
3. Create conversion for uploading images to side server including outputting thumbnails
4. Modify restaurant page to support images, possibly create pop up for slideshow on images
5. Allow restaurants to be able to choose their main avatar and if they have only 1 picture automatically choose that as the first picture.
6. Review the restaurant page on basic functionality such as follow/unfollow, create a review as a anonymous user or logged in, claim restaurant, and contact restaurant.
7. Create the PPC Adwords page and integrate keyword based data input to attribute to the ppc adwords campaign. Update API code to support the additional keywords users may want to find a business for.
8. Finish promotional and coupon administration page development and add the data to be displayed on restaurant page. Also follower feeds.
9. Create a list based restaurant lookup with a small side map of restaurants listed. Create the pagination based on JavaScript and not reloading the page.
10. Update the customer feed to allow restaurant promotions and deals to be viewed and displayed
11. Update customer profiles to display their user data and allow them to upload an avatar.
12. Update the home page for mobile optimization. Not displaying restaurants on the home page but displaying categories and things they might be interested in.
13. Update the map view page to show recently opened restaurants and save it in cookies not database.
14. Update the business page to create a more efficient marketing layout
15. Finish the subscription signup and payout. Make sure I also add somewhere in the admin for businesses to let them know when their subscription expires.
16. Update the support page for a JavaScript based search and display function for people's FAQ. Also allow them to submit email until further support development can be made.